## Project Planner
Project Planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
Feature | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Login | 1 | 5 | 1 | 4 | 100% | bar: PERIODS 1 to PERIODS 2; PERIODS 5 to PERIODS 7
Logout | 1 | 6 | 1 | 6 | 100% | bar: PERIODS 1 to PERIODS 2; PERIODS 7
Create Account | 2 | 4 | 2 | 5 | 100% | bar: PERIODS 1 to PERIODS 2; PERIODS 6 to PERIODS 7
Delete Accounts | 4 | 8 | 4 | 6 | 100% | bar: PERIODS 1 to PERIODS 3; PERIODS 5 to PERIODS 8
Search Items | 4 | 2 | 4 | 8 | 0% | bar: PERIODS 4 to PERIODS 8; PERIODS 10 to PERIODS 11
Post Items | 4 | 3 | 4 | 6 | 90% | bar: PERIODS 6 to PERIODS 8
Delete Items | 5 | 4 | 5 | 3 | 0%
Purchase Item | 5 | 2 | 5 | 5 | 0% | bar: PERIODS 7 to PERIODS 8
User Profile | 5 | 2 | 5 | 6 | 80% | bar: PERIODS 3 to PERIODS 4; PERIODS 7 to PERIODS 8; PERIODS 10
Ratings | 6 | 5 | 6 | 7 | 0% | bar: PERIODS 6 to PERIODS 8; PERIODS 10 to PERIODS 12
Add pictures | 6 | 1 | 5 | 8 | 100% | bar: PERIODS 4 to PERIODS 5; PERIODS 7; PERIODS 10 to PERIODS 12
Sorting | 9 | 3 | 9 | 3 | 0% | bar: PERIODS 10 to PERIODS 11
Chinese | 9 | 6 | 9 | 7 | 0% | bar: PERIODS 10 to PERIODS 15
Turkish | 9 | 3 | 9 | 1 | 0%
Dark Mode | 9 | 4 | 8 | 5 | 90% | bar: PERIODS 3 to PERIODS 8; PERIODS 10 to PERIODS 12
Smooth Interface | 10 | 5 | 10 | 3 | 40% | bar: PERIODS 3 to PERIODS 8; PERIODS 10 to PERIODS 12